talvexIT

Australia Go-to-Market & Growth Marketing Plan

An IT Services Marketplace Platform

Plan Period: 12 Months  |  Market: Australia

Prepared: May 2026

# Contents

1. Executive Summary

2. Market Context & Opportunity

3. Positioning & Brand Narrative

4. Target Audience Segments

5. Marketing Objectives & KPIs

6. Strategic Pillars

7. Channel Plans

7.1 LinkedIn

7.2 YouTube

7.3 Instagram

7.4 Facebook

7.5 X (Twitter)

7.6 TikTok

7.7 Reddit & Community Forums

7.8 SEO & Content Marketing

7.9 Email & Lifecycle Marketing

7.10 Paid Search (Google Ads)

8. Content Calendar Framework

9. Partnerships, PR & Events

10. Budget Allocation

11. 90-Day Launch Roadmap

12. Measurement & Reporting

13. Risks & Mitigations

# 1. Executive Summary

talvexIT enters the Australian market as a two-sided IT services marketplace, connecting Australian businesses (SMBs, mid-market and enterprise buyers) with vetted IT service providers, contractors and specialist talent. The platform competes in a category dominated globally by Upwork, Fiverr, Freelancer.com and Toptal, but differentiates through local trust, curated quality, IT-specific workflows and Australian compliance readiness.

This plan sets out a 12-month integrated marketing strategy across digital, social, content, partnership and PR channels. It is designed to be executed by a small founding marketing team (2–3 people) supported by freelance creators and agency partners, with a recommended initial annual budget of AUD 240,000–360,000 (approx. AUD 20–30k per month).

### Headline Targets (Year 1)

| Metric | Target | Rationale |
| --- | --- | --- |
| Registered buyers | 3,500 | Sufficient demand density for healthy supply utilisation |
| Verified IT providers/freelancers | 1,200 | ~3:1 buyer:provider ratio supports liquidity |
| Gross Marketplace Volume (GMV) | AUD 4.5M | Conservative based on AUS gig+IT services TAM |
| Website monthly visitors (Mo. 12) | 55,000 | Built via SEO, social, paid and PR |
| LinkedIn followers | 10,000 | Primary channel for B2B credibility |
| Email list | 12,000 segmented contacts | Owned channel, foundation of lifecycle |
| Brand-aided awareness (Sydney/Melbourne SMB) | 15% | Measured via 2 brand surveys (Mo. 6 + Mo. 12) |

# 2. Market Context & Opportunity

## 2.1 Why Australia, Why Now

- The Australian IT services market is forecast to grow from approximately AUD 38 billion in 2026 to AUD 91 billion by 2031, an 18.9% CAGR. Cloud and platform services lead the growth at ~23% CAGR.

- Cybersecurity, cloud migration and AI-readiness are top spend categories, particularly under the federal government's Essential Eight uplift programs.

- Sydney and Melbourne together account for more than half of Australian IT services spend; Perth, Brisbane and Canberra are fast-rising secondary markets.

- Australia's freelance platforms market reached approximately USD 240M in 2024 and is forecast to grow to USD 611M by 2030 (17.6% CAGR), driven by SMB demand for flexible specialist talent.

- Over a third of the Australian workforce already engages in some form of freelance or independent work, with a strong tilt toward digital and IT skills.

## 2.2 Competitive Landscape

| Competitor | Strength | Weakness vs. talvexIT |
| --- | --- | --- |
| Upwork | Global supply, brand recognition, AI matching | Generalist, low signal-to-noise for IT buyers, weak local trust |
| Freelancer.com (AU HQ) | Local origin, scale, brand familiarity | Race-to-the-bottom pricing, low-quality perception in IT |
| Fiverr | Productised gigs, design/marketing-heavy | Limited fit for complex IT services and managed engagements |
| Toptal | Premium IT/dev talent, vetted | High price point, US-centric, limited SMB appeal |
| Expert360 (AU) | Local consulting/strategy talent | Narrow to consulting, not IT-services-first |
| Local IT consultancies / MSPs | Trust, end-to-end delivery | Slow, expensive, limited bench for niche skills |

talvexIT's wedge: an IT-services-first marketplace built for Australia. Curated supply, scoped statements of work, GST-correct invoicing, milestone escrow, and compliance-friendly contracting that enterprise procurement teams will accept.

# 3. Positioning & Brand Narrative

### Positioning Statement

For Australian businesses that need specialised IT capability fast, talvexIT is the trusted local marketplace that connects you with vetted IT providers and freelancers — with Australian compliance, transparent pricing, and milestone-based delivery built in. Unlike global generalist platforms, talvexIT is purpose-built for IT services and the way Australian businesses actually buy them.

### Brand Pillars

- Local trust: Australian-vetted providers, GST-compliant invoicing, local dispute resolution.

- IT-first: Workflows, scoping templates and matching designed for IT services — not generic gigs.

- Quality, curated: Capability verification, references and review integrity over volume.

- Outcome-based delivery: Milestone escrow, statement-of-work tooling, and project guardrails.

- Speed: From scope to shortlist in under 48 hours.

### Tone of Voice

Confident, plain-English, pragmatic. No buzzwords. We sound like a senior consultant who happens to be friendly — not a Silicon Valley pitch deck.

### Tagline Options (for testing)

- "IT done right. Locally."

- "Australia's IT services marketplace."

- "Vetted IT talent, on demand."

- "Scope it. Match it. Ship it."

# 4. Target Audience Segments

## 4.1 Demand Side (Buyers)

| Segment | Typical Buyer | Top Needs | Priority |
| --- | --- | --- | --- |
| SMB (10–199 staff) | Owner / Ops Manager / non-technical founder | Web, cloud, cybersecurity uplift, IT support, AI tooling | Tier 1 — primary launch focus |
| Mid-market (200–999 staff) | IT Manager / Head of IT / Procurement | Project-based dev, integrations, data, cyber, augmentation | Tier 1 — primary launch focus |
| Enterprise (1,000+ staff) | Vendor Manager / CIO office / PMO | Pre-vetted contractor pools, SoW-based engagements | Tier 2 — Year 1 H2 onwards |
| Government / Public sector | Procurement officer | Panel-adjacent contractors, security-cleared talent | Tier 3 — Year 2 |
| Agencies & consultancies | MD / Delivery lead | Subcontract specialist skills (white-label) | Tier 2 — partner channel |

## 4.2 Supply Side (Providers)

| Segment | Description | Acquisition Hook |
| --- | --- | --- |
| Independent IT contractors | Senior devs, cloud, cyber, data, AI specialists going solo | Higher-quality leads, fair fees, AU-paying clients |
| Boutique IT firms (2–20 people) | Specialist consultancies needing pipeline | Procurement-friendly storefront, no BD overhead |
| MSPs & systems integrators | Established IT services businesses | Overflow work, niche skills, partner program |
| Tech graduates & juniors | University leavers, bootcamp grads | Verified portfolio building, mentor-led gigs |

## 4.3 Persona Snapshots

### Buyer — "Operations Manager Olivia" (SMB, Sydney)

- 38, runs ops at a 60-person professional services firm.

- Needs to fix Microsoft 365 security, build a client portal, and find ongoing IT support.

- Currently relies on word-of-mouth referrals and one over-stretched MSP.

- What she wants from talvexIT: A shortlist of 3 vetted providers, fixed-price quotes, and someone she can call if it goes wrong.

### Buyer — "Head of IT Hugh" (Mid-market, Melbourne)

- 45, manages a team of 12 across infra, apps and security.

- Needs to augment with cloud and cybersecurity contractors for 6–12 month engagements.

- Frustrated by recruitment agency fees and slow time-to-fill.

- What he wants from talvexIT: Faster shortlists than agencies, transparent rates, compliance handled.

### Provider — "Contractor Chris" (Independent, Brisbane)

- Senior cloud architect, 14 years' experience, recently went independent.

- Wants steady AU-paying work without recruiter middlemen.

- What he wants from talvexIT: Quality leads, fair commission, fast payouts, professional clients.

# 5. Marketing Objectives & KPIs

The plan ladders up to four primary marketing objectives, each with measurable KPIs reviewed monthly.

| Objective | Primary KPI | Year 1 Target | Lead Indicator |
| --- | --- | --- | --- |
| Build category awareness in AU | Branded search volume, share of voice | 5,000 monthly branded searches | Press mentions, social reach |
| Acquire qualified buyers | Buyer sign-ups → first project posted | 3,500 sign-ups, 35% post a project | Landing page conversion rate |
| Acquire quality providers | Verified provider profiles | 1,200 verified | Application volume × pass rate |
| Drive marketplace liquidity | GMV and project completion rate | AUD 4.5M GMV; 70% completion | Match rate; time-to-first-message |

### North Star Metric

Weekly Active Matched Projects — the number of projects each week where a buyer has contacted at least one provider and received a response. This single metric captures both supply and demand health.

# 6. Strategic Pillars

### Pillar 1 — Trust as the Wedge

Our biggest enemy is buyer scepticism: 'Will they actually deliver? Are they real? What if it goes wrong?' Every channel must answer this. Tactics: provider verification badge, public case studies, named founder presence, AU office address, milestone escrow as a marketing message.

### Pillar 2 — Demand-Led Supply Growth

In two-sided marketplaces, supply without demand churns. We grow buyers first in target verticals (professional services, retail/e-commerce, healthcare), then recruit providers to match the demand we see. Provider acquisition is always 4–6 weeks ahead of demand acquisition in the same skill area.

### Pillar 3 — Content That Earns Search

IT buying questions are highly searched and poorly answered. We will own the AU long-tail with practical, opinionated content: "How much does a Shopify migration cost in Australia?", "Essential Eight checklist for SMBs", "Hiring a contract React developer in Melbourne". Content is the moat.

### Pillar 4 — Founder-Led Distribution

Early-stage marketplaces grow on the back of a visible, opinionated founder. The CEO (or a designated executive) builds a personal brand on LinkedIn from week one — sharing market data, lessons, customer stories. This is non-negotiable.

### Pillar 5 — Partnerships Over Paid

Paid acquisition is expensive in B2B IT. We over-invest in partnerships: industry associations, accountants, MSPs, accelerators, universities. Each partner is a distribution channel.

# 7. Channel Plans

Each channel below has a defined role, audience, content mix, posting cadence, KPIs and indicative monthly budget. Channels are tiered by priority for the first 12 months.

### Channel Priority Tiers

| Tier | Channels | Role |
| --- | --- | --- |
| Tier 1 — Lead | LinkedIn, SEO/Content, Email | Primary B2B credibility & demand engines |
| Tier 2 — Amplify | YouTube, Google Ads, Reddit/Communities | Reach, intent capture, peer trust |
| Tier 3 — Test | Instagram, Facebook, X (Twitter), TikTok | Audience expansion, employer brand, cultural reach |

## 7.1 LinkedIn — Tier 1 (Lead)

- Role: Primary B2B awareness, founder voice, provider recruitment.

- Audience: IT decision-makers, procurement, ops leaders, contractors.

- Cadence: Company page 4×/week; founder profile 4–5×/week; 1 LinkedIn newsletter every 2 weeks.

- Monthly budget: AUD 4,000 (AUD 2,500 paid + AUD 1,500 creative/freelance writer).

### Content Mix (per week)

| Format | Frequency | Example |
| --- | --- | --- |
| Founder POV post | 2× per week | "3 reasons most Shopify migrations blow their budget — and how to scope yours properly." |
| Customer/case study | 1× per week | "How [Company] cut their cloud bill by 38% with a contractor from talvexIT." |
| Market data / chart | 1× per week | AU IT services growth, hiring trends, salary benchmarks. |
| Provider spotlight | 1× per fortnight | Featured contractor / boutique firm, with their POV. |
| Carousel guide | 1× per fortnight | Visual checklist (e.g. "Essential Eight in 9 slides"). |
| Newsletter | 1× per fortnight | "The talvexIT Brief" — AU IT market roundup. |

### KPIs

- Company page followers: 10,000 by Month 12 (start ~0)

- Average post engagement rate: ≥4%

- Inbound leads via LinkedIn (form fills + DMs): 60+/month by Month 12

- Founder profile followers: 8,000+

### Paid Plays

- Sponsored Content boosting top organic posts (1–2 per week)

- Lead-gen forms targeting AU IT Managers + Operations Managers in 50–500 employee firms

- Conversation Ads to providers (Senior IT contractors, AU-only)

## 7.2 YouTube — Tier 2 (Amplify)

- Role: Long-form trust, SEO compound asset, sales enablement.

- Audience: Buyers researching how to scope IT projects; providers evaluating the platform.

- Cadence: 1 long-form video (8–15 min) per week + 2–3 Shorts per week.

- Monthly budget: AUD 3,500 (production + editor + thumbnail designer).

### Series / Show Concepts

| Series | Format | Why it Works |
| --- | --- | --- |
| "What it really costs" | Cost-breakdown explainers (e.g. CRM build, mobile app, cloud migration) | Hits high-intent search queries, builds buyer trust |
| "Inside the project" | Mini case studies with real customers (3–5 min) | Social proof at scale; reusable across channels |
| "Provider Q&A" | Live and recorded Q&As with top providers | Recruits providers, educates buyers, reusable Shorts |
| "AU IT Pulse" | Monthly market roundup (data + commentary) | PR worthy, builds founder thought leadership |

### KPIs

- Subscribers: 5,000 by Month 12

- Watch time: 60,000 hours cumulative

- Average view duration on long-form: ≥45%

- Click-through to talvexIT.com: ≥3% of views

## 7.3 Instagram — Tier 3 (Test)

- Role: Employer brand, behind-the-scenes, provider community.

- Audience: Younger IT professionals, design-led founders, cultural reach.

- Cadence: 3 feed posts/week, 4 stories/week, 2 Reels/week.

- Monthly budget: AUD 1,500 (mostly creative; minimal paid until month 6).

### Content Mix

- Reels: "day in the life" of a contractor; quick tips ("3 signs you need a cybersecurity audit")

- Carousels: data visualisations, checklists, salary benchmarks

- Stories: customer wins, polls, team moments

- Quote cards from founders, providers and customers

### KPIs

- Followers: 4,500 by Month 12

- Reels average plays: ≥2,500

- Engagement rate: ≥3.5%

## 7.4 Facebook — Tier 3 (Test)

- Role: SMB owner reach, community groups, retargeting.

- Audience: SMB owners 35–60, tradies-turned-business-owners, regional Australia.

- Cadence: 2 page posts/week + active participation in 6–8 SMB Facebook Groups.

- Monthly budget: AUD 1,500 (paid retargeting heavy).

### Tactics

- Repurpose LinkedIn carousels and customer stories

- Run retargeting ads to website visitors who didn't convert

- Sponsor relevant AU SMB Facebook Groups (e.g. "Australian Small Business Owners")

- Monthly Facebook Live AMAs with the founder

### KPIs

- Page followers: 2,500

- Retargeting CTR: ≥1.2%

- Cost per landing page view (retargeting): <AUD 1.50

## 7.5 X (Twitter) — Tier 3 (Test)

- Role: Tech and developer community, real-time market commentary, PR amplification.

- Audience: AU tech founders, developers, journalists, VCs.

- Cadence: Founder posts 1–2×/day; brand account 3×/week.

- Monthly budget: AUD 500 (mostly organic; small paid for launches).

### Tactics

- Founder thread per fortnight unpacking AU IT market data

- Real-time commentary on AU tech news (Telstra, MYOB, Atlassian, govt cyber)

- Reply-guy strategy: meaningful replies on posts from AU tech press, founders, analysts

- Coordinate launches and reports here for PR pickup

### KPIs

- Founder followers: 5,000

- Average impressions/post: ≥3,000

- Press / podcast inbound from X: 6+ in Year 1

## 7.6 TikTok — Tier 3 (Test)

- Role: Reach younger IT professionals, future contractors, cultural credibility.

- Audience: 18–34 tech-curious, university students, early-career IT, freelance-curious.

- Cadence: 3–5 short videos/week. Test for 6 months, double down or cut.

- Monthly budget: AUD 1,000 (creator-led).

### Content Mix

- "How much do AU IT contractors actually earn?" (data-led explainers)

- Quick day-in-the-life videos with featured providers

- Career-path content: "Bootcamp grad to AUD 800/day contractor"

- Trend hijacking — only when authentic to IT/business audience

### KPIs

- Followers: 5,000 (Stretch: 10k)

- Average video views: ≥3,000

- 3+ videos hitting 100k+ views in Year 1

## 7.7 Reddit & Community Forums — Tier 2 (Amplify)

- Role: Authentic peer-to-peer trust building, support, technical credibility.

- Audience: Developers, sysadmins, IT professionals, AU SMB owners.

- Cadence: Genuine participation 3–5×/week across target subreddits and forums.

- Monthly budget: AUD 500 (community manager time).

### Target Communities

- r/AusFinance, r/smallbusinessAU — buyer side

- r/sysadmin, r/cscareerquestionsAU, r/auscorp — provider side

- Whirlpool forums (Australian tech forum)

- Slack and Discord communities for AU developers (e.g. SydJS, MelbCSS)

### Rules of Engagement

- Never post promotional content; always disclose affiliation when relevant

- Run AMAs only after 3+ months of genuine community participation

- Mods of small subreddits should be approached for sponsored AMAs / surveys

## 7.8 SEO & Content Marketing — Tier 1 (Lead)

- Role: Compound demand engine, intent capture, brand authority.

- Audience: All buyer and provider segments at research stage.

- Cadence: 2 long-form articles/week + monthly data report + ongoing programmatic pages.

- Monthly budget: AUD 6,000 (writers, SEO tools, technical SEO contractor).

### Content Pillars

| Pillar | Examples | Stage |
| --- | --- | --- |
| Cost guides (AU) | "How much does X cost in Australia in 2026" | Top of funnel — high search volume |
| Hiring guides | "How to hire a [skill] contractor in Australia" | Mid funnel — buyer intent |
| Compliance & frameworks | Essential Eight, Privacy Act, GDPR for AU | Mid funnel — trust building |
| Salary & rate benchmarks | Annual AU IT contractor rates report | Top + bottom funnel — links + leads |
| Comparison pages | talvexIT vs Upwork / Freelancer / agency | Bottom funnel — conversion |
| Programmatic location pages | "Hire a [skill] contractor in [city]" | Long-tail SEO scale |

### KPIs

- Organic monthly visitors: 30,000 by Month 12

- Ranking keywords (top 10): 1,500

- Backlinks from DR 50+ sites: 80+ in Year 1

- Organic-attributed sign-ups: 800+/month by Month 12

## 7.9 Email & Lifecycle Marketing — Tier 1 (Lead)

- Role: Owned channel, nurture, retention, marketplace activation.

- Audience: All registered users + opt-in newsletter list.

- Cadence: Weekly newsletter + behaviour-triggered lifecycle flows.

- Monthly budget: AUD 1,500 (ESP, copywriter, design).

### Core Programs

| Program | Trigger | Goal |
| --- | --- | --- |
| Buyer welcome series | Sign-up | Post first project within 7 days |
| Provider onboarding series | Verification submitted | Complete profile + first proposal |
| Project nudge | Project posted but no message in 48h | Drive first message |
| Win-back | Inactive 30 days | Reactivate with new market data + featured providers |
| The talvexIT Brief (newsletter) | Weekly | Thought leadership, retention, share-out |
| Quarterly Rate Report | Quarterly | PR, leads, list growth |

### KPIs

- List size: 12,000 segmented contacts

- Newsletter open rate: ≥40%

- Lifecycle flows: ≥25% click-through on activation emails

- Email-attributed projects posted: 25%+ of total

## 7.10 Paid Search (Google Ads) — Tier 2 (Amplify)

- Role: High-intent demand capture, brand defence, geo-targeted SMB acquisition.

- Audience: Buyers actively searching for IT services and contractors.

- Cadence: Always-on; weekly optimisation.

- Monthly budget: AUD 5,000 (scaling to AUD 8,000 by Month 12).

### Campaign Structure

| Campaign | Match Type | Indicative CPC (AU) | Expected Role |
| --- | --- | --- | --- |
| Brand defence (talvexIT) | Exact / phrase | AUD 0.30–0.80 | Capture branded searches; cheap |
| Competitor (Upwork, Freelancer) | Phrase | AUD 3–6 | Steal consideration traffic |
| Hire a [skill] contractor AU | Phrase | AUD 6–14 | Core buyer intent |
| IT services [city] | Phrase / location | AUD 5–10 | SMB local intent |
| Cost-guide retargeting (Display) | Audience | AUD 0.50–1.50 | Re-engage blog readers |

### KPIs

- Cost per qualified buyer sign-up: ≤AUD 65

- Cost per first project posted: ≤AUD 180

- ROAS on payback basis: 12-month payback by Month 9

# 8. Content Calendar Framework

A weekly rhythm keeps the team disciplined and ensures every channel feeds the others. The flagship piece each week is the long-form article or video — everything else is repurposed from it.

### Weekly Rhythm

| Day | Action | Channels |
| --- | --- | --- |
| Monday | Publish flagship long-form (article or YouTube video) | Website, YouTube |
| Monday | Founder LinkedIn POV post tied to flagship | LinkedIn |
| Tuesday | Repurpose flagship into LinkedIn carousel + Instagram carousel | LinkedIn, Instagram |
| Wednesday | Customer story / case study post | LinkedIn, Facebook, Email |
| Wednesday | Send weekly newsletter "The talvexIT Brief" | Email |
| Thursday | Reels / Shorts / TikTok cuts from flagship video | Instagram, TikTok, YouTube Shorts |
| Thursday | Founder X thread on weekly topic | X (Twitter) |
| Friday | Provider spotlight + community engagement | LinkedIn, Reddit, Instagram |
| Saturday/Sunday | Light: scheduled stories, reply-only on socials | All |

### Monthly Themes (Year 1)

| Month | Theme | Anchor Content |
| --- | --- | --- |
| Month 1 | Launch & manifesto | Founder launch essay; press release; "Why talvexIT" video |
| Month 2 | Cost transparency | AU IT services cost benchmark report |
| Month 3 | Cybersecurity & Essential Eight | SMB Essential Eight checklist; webinar |
| Month 4 | Cloud migration | Migration cost calculator; case studies |
| Month 5 | AU contractor rates | Quarterly rates report (PR push) |
| Month 6 | Hiring vs. contracting | Decision framework; CFO-targeted content |
| Month 7 | AI & automation | Practical AI buying guide for SMBs |
| Month 8 | Cybersecurity (back to school) | Updated Essential Eight; new webinar |
| Month 9 | Quarterly rates report v2 | PR, list growth |
| Month 10 | End of year IT planning | FY26/27 IT budget guides |
| Month 11 | Customer awards / wins | "Project of the Year" community vote |
| Month 12 | Year in review + 2027 outlook | Big data report; founder predictions piece |

# 9. Partnerships, PR & Events

## 9.1 Partnership Targets

| Partner Type | Examples | Value Exchange |
| --- | --- | --- |
| Industry associations | ACS (Australian Computer Society), AIIA, COSBOA | Member discount; co-branded research |
| Accountants & advisors | Xero / MYOB partner network, BDO, Grant Thornton | Referral fees; co-marketed SMB guides |
| MSPs (overflow partners) | Mid-tier AU MSPs | Subcontract pipeline; revenue share |
| Universities / bootcamps | UTS, Monash, RMIT, General Assembly, Coder Academy | Junior provider pipeline; talent stories |
| Cloud vendors | AWS, Microsoft, Google Cloud (AU teams) | Co-marketing; partner directory presence |
| Accelerators / VC firms | Startmate, Antler, Blackbird, Square Peg | Portfolio discount; founder distribution |

## 9.2 PR Strategy

- Hire a fractional AU tech PR consultant (AUD 3,500/month) from Month 1

- Two flagship press moments per year: launch (Month 1) + Series A or growth milestone

- Quarterly data reports as press hooks (rates, hiring trends, AI adoption)

- Target outlets: AFR, SmartCompany, ITNews, CRN Australia, Startup Daily, The Australian (Tech), Capital Brief

- Founder podcast tour: 12 podcasts in Year 1 (Aussie startup, business, IT)

## 9.3 Events

| Event | City | Role |
| --- | --- | --- |
| SXSW Sydney | Sydney | Founder speaking + branded side event |
| AISA CyberCon | Melbourne | Sponsorship; provider recruitment |
| Atlassian Team / Pause Fest | Sydney/Melbourne | Side events; founder networking |
| State Chambers of Commerce events | All states | SMB buyer acquisition |
| talvexIT Roundtables (own) | Sydney + Melbourne quarterly | 20-person CIO/IT-Manager dinners |

# 10. Budget Allocation

Indicative Year 1 marketing budget: AUD 312,000 (AUD 26,000/month average). Front-loaded: heavier in Months 1–3 for launch, then steady-state with optimisation.

### Annual Budget by Channel

| Channel / Line Item | Monthly (AUD) | Annual (AUD) | % of Total |
| --- | --- | --- | --- |
| SEO & Content (writers, tools, tech) | 6,000 | 72,000 | 23% |
| Google Ads (paid search) | 5,000 | 60,000 | 19% |
| LinkedIn (organic + paid) | 4,000 | 48,000 | 15% |
| YouTube production | 3,500 | 42,000 | 13% |
| PR & comms (fractional) | 3,500 | 42,000 | 13% |
| Email & lifecycle | 1,500 | 18,000 | 6% |
| Instagram + creative | 1,500 | 18,000 | 6% |
| Facebook + retargeting | 1,500 | 18,000 | 6% |
| TikTok (test budget) | 1,000 | 12,000 | 4% |
| X (Twitter) + Reddit/communities | 1,000 | 12,000 | 4% |
| Events & partnerships | 2,500 | 30,000 | 10% |
| Tools (analytics, ESP, CRM, design) | 1,000 | 12,000 | 4% |
| Total | 32,000* | 384,000* | — |

*Total reflects the full target operating budget. A leaner launch budget of AUD 240,000 (AUD 20,000/month) is achievable by reducing TikTok, paid Facebook, and event spend in the first 6 months and scaling up once channel ROI is proven.

### Headcount (separate from media spend)

| Role | FTE/Contractor | Year 1 Cost (AUD) |
| --- | --- | --- |
| Head of Marketing / Growth Lead | 1.0 FTE | 160,000 |
| Content & SEO Lead | 1.0 FTE | 110,000 |
| Social Media & Community Manager | 1.0 FTE | 85,000 |
| Video editor (contract) | 0.5 FTE | 45,000 |
| Designer (contract) | 0.4 FTE | 35,000 |
| Total marketing headcount | — | 435,000 |

# 11. 90-Day Launch Roadmap

### Days 1–30: Foundation

- Finalise brand, positioning, voice, visual system

- Launch website with 10 cornerstone SEO articles already published

- Set up analytics: GA4, Mixpanel, attribution model, dashboards

- Stand up CRM, email platform, social scheduling tool

- Founder LinkedIn warm-up: 30 days of consistent posting before launch

- Brief AU PR consultant, prepare launch press kit

- Recruit first 100 providers as founding members (free verification)

### Days 31–60: Launch

- Public launch: PR push, founder essay, press release, podcast tour starts

- Activate Google Ads, LinkedIn paid, Facebook retargeting

- First flagship report published (AU IT cost benchmark)

- Run first "Provider AMA" on Reddit and LinkedIn Live

- First 3 founder roundtable dinners booked (Sydney + Melbourne)

- Daily monitoring: sign-ups, project posts, match rate, NPS

### Days 61–90: Optimise

- First channel attribution review — kill or scale based on data

- Launch referral program for buyers and providers

- Publish first customer case studies (target: 5)

- Start TikTok and YouTube Shorts experiments

- First quarterly rates report drafted for Month 5 release

- Brand awareness baseline survey conducted

# 12. Measurement & Reporting

### Reporting Cadence

| Cadence | Audience | Contents |
| --- | --- | --- |
| Daily | Marketing team | Sign-ups, projects posted, ad spend, top-line traffic |
| Weekly | Marketing + product leadership | Channel performance, content performance, paid CAC |
| Monthly | Executive team | Full funnel, marketplace health, GMV, NPS, channel ROI |
| Quarterly | Board / investors | Strategy review, brand health, roadmap adjustments |

### Key Dashboards

- Acquisition: traffic by source, sign-ups, CAC by channel, paid efficiency

- Activation: % posting first project, time-to-first-project, time-to-first-message

- Marketplace health: matched-project rate, response time, completion rate, NPS

- Content: top organic pages, keyword rankings, backlink growth, video retention

- Brand: branded search volume, social share of voice, awareness survey

### Attribution

Use a multi-touch attribution model (linear with last-touch override) for paid channels, and self-reported attribution ("How did you hear about us?") at sign-up for organic and brand. Triangulate quarterly with a brand-lift study to validate dark-funnel impact of LinkedIn and PR.

# 13. Risks & Mitigations

| Risk | Likelihood | Mitigation |
| --- | --- | --- |
| Cold-start: not enough providers when buyers arrive | High | Recruit 100 founding providers before public launch; concierge-match the first 200 projects |
| Cold-start: not enough buyer demand | High | Lead with content + founder distribution; offer free first project for early buyers |
| Quality incidents (a project goes badly) | Medium | Milestone escrow; published dispute process; AU-based support |
| Larger competitor enters or undercuts | Medium | Lock in via provider exclusivity perks, AU compliance advantage, partnership moats |
| Paid channels too expensive for B2B IT | Medium | Over-invest in SEO, PR and partnerships; treat paid as accelerant, not engine |
| Founder bandwidth for content | High | Use a ghostwriter for LinkedIn drafts; record podcast-style audio that team turns into posts |
| Privacy / Australian Consumer Law issues | Low–Medium | Legal review of marketplace T&Cs; transparent data handling; no dark-pattern marketing |

This plan is a living document. The first 90 days will reveal which channels punch above their weight and which underperform. The team should treat the budget allocation as a starting hypothesis to be re-tested each quarter.